|  | Activities 2006 | Timeline |  | Contents and Presenters | Lead Agency |
| --- | --- | --- | --- | --- | --- |
|  |  | Planned | Actual |  |  |
| 1 | Law on Association | Q1-Q2 | 15 May | Objective: Information sharing. Update members of the latest draft law, associated pros and cons, and provide comments and inputs to MoHA on the draft law. Presenter: Mr. Hoang Ngoc Giao, LERES | UNDP, VNAH, Oxfam |
| 2 | Proposal for National Volunteer Centre in Vietnam | Q1 | 17Feb | Introduction of the National Volunteer Centre model in Vietnam, Suggestion by Koen Van Acoleyen, UN Volunteer Centre | Koen Van Acoleyen, UN Volunteer Centre |
| 3 | Status of Civil Society in Vietnam and how to strengthen civil society | Q2 | June | Objective: Strengthening of networks between organisations. Presentation of CIVICUS CSI project and the suggestions for strengthening CS. Discussions among VNGOs, INGOs and other practitioners. Irene Norlund and Prof. Dang Ngoc Dinh, VIDS, (national project coordinator) or team member for instance Nguyen Manh Cuong from VUSTA, Dang Ngoc Quang, RCRD Comments from VNGOs and INGOs | Irene, UNDP |
| 4 | List of members update | Q1-Q2 |  |  | TTHai (CARE) |
| 5 | Update of e-list | Q1-Q2 |  |  | TTHai (CARE) |
| 6 | Plan project for participatory models | Q2-Q3 |  |  | TTHai (CARE) |
| 7 | Meeting with MOHA, ambassadors and PPWG on the draft law on associations | Q2 | 3 April |  | TTHai (CARE) |
| 8 | Launch of CIVICUS civil society index study | Q2 | 9 May |  | TTHai (CARE) |
| 9 | Finland Embassy engaged in GDD seminar in June with two surveys: Mekong Economics, Indicators for GDD and support for GDD by local fund | Q2-Q3 |  |  | TTHai (CARE) |
| 10 | UNDP project by McElwee and others about GDD and participatory governance presented | Q2 |  |  | TTHai (CARE) |
| 11 | SEDP –how do INGOs and NGO participate in implementation? |  |  | Objective: To make a status about the changes that the SEDP might bring about and what it means for the influence of the organisations – INGOs and VNGOs on government policy and improvement of participatory governance. How are the links between GDD and participatory governance at higher levels? Regulations and concrete experiences. | Hoa (OGB) Invitation to participate: MPI, MARD, Oxfam GB Chia Se, SNV |
| 12 | Draft decree about Rural Collaboration Groups and study about RCG. Combine it with discussion of network | Q4 | Nov | Objective: Information sharing and suggestions for step forward. Follow up on discussions from 2005 on RCG and networking among CSOs | Hai (CARE), Hoa (OGB), Tung (IFAD), Huong (FE). |