GCAP meeting at the NGO RC 18/08

Meeting minute

GCAP 2006

Short introdcution of GCAP by Trine, NRC and Chau, AAV.

For GCAP 2006 in Vietnam the core group, consisting of 4 INGOs active from 2005, VUFO and the NGO RC, proposes that GCAP 2006 VN focuses on the two following issues:

1) Trade Justice

- trade protectionism (from the developed countries)

- trade pressure (VN will soon enter WTO, intellectual property right, etc.)

- promote pro-poor trade policies

2) Poverty Alleviation (Governance)

- grassroots decree, the decree is there, but the implementation is slow

- budget transparency process, which is linked to anti-corruption

- child rights

- quality and enforcement of the Gender Equality and Domestic Violence Laws,

- promote the participation of CSOs in the anti-corruption

Proposed Activities

The matrix of activities developed by the core group was presented and discussed. One point raised was that if you really want to raise awareness and make and impact, you should focus on two or maximum three issues, given the limited set of activities. The participants agreed that this years GCAP Vietnam shall focus on 1) Trade justice, and 2) Anti-corruption. While it was proposed that child rights issues should be in focus next year, at which point the new Child Rights Working Group could play an active role.

It was discussed which NGO would be interested in taking part in which activities and agreed that on INGO should take the lead, while obviously VUFO still remains responsible for the activities as already agreed at an earlier meeting. The lead INGO may support VUFO in the process of developing the TOR, based on the input from all INGOs taking part in the particular activity. In the attached matrix it is indicated, what activities the different INGOs want to take part in (the INGO in bold is the lead INGO).

Save the Children UK and will investigate if the organisations are able to make financial contributions. They will feed back within one week.

AAV is the overall financial coordinator

NRC is responsible of information dissemination and communication etc.

Action Points

1) NRC will inform VUFO of meeting outcome

2) NRC will sends out: matrix, TOR content outline, TORs for 1,4,8, and contact details of mr. Tuong, PACCOM

3) Each sub-groups will prepare or finalise TORs for their activity.

4) Comments on the TORs for activity 1,4, and 8 should be sent to the NRC by the 25/8 is deadline for comments.

5) Deadline for drafting the ToRs for 2,3,5,6 is the 25/8

6) Status of the GCAP VN shall be presented at the INGO forum on the 8/9, by one of the core group members

7) Next meeting GCAP meeting will be the 14. september (tentative), NRC will announce