Committee for Ethnic Minority Affairs

2007 Work Plan for Program 135

| No. | PRODUCTS/RESULTS | MAIN ACTIVITIES | Quarter | Lead | Coordina-ting |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 |  |  |
| I – Program management |
| 1 | List of communes and villages to be included in P135-II | - Review the list for 2007. - Prepare draft Prime Minister’s Decision approving the additional list of communes and villages to be included in P135-II. - Prepare draft Prime Minister’s Decision approving the additional list of communes obtaining P135-II targets. | X X X | X X X |  |  | CEM | MPI |
| 2 | Criteria for communes and villages accomplishing P135-II targets and developing investment plan for 2008 | - Research to develop the criteria. - Develop guidelines for reviewing communes and villages obtaining P135-II targets - Prepare draft Prime Minister’s Decision approving the list of communes obtaining P135-II targets. - Prepare Investment Plan for 2008. | X X | X X |  | X X | CEM | MPI |
| 3 | Guidelines for budget allocation criteria under P135-II | - Research to develop guidelines for budget allocation for P135-II based on the criteria. - Guide the localities to implement budget allocation under P135-II based on the criteria and local conditions. | X X | X X |  |  | CEM |  |
| 4 | Guidelines for financial management and reporting under P135-II. | - Provide training in the State Treasury’s Circular (integrated with other aspects in a training course) |  | X |  |  | MOF | CEM |
| 5 | ODA for P135-II accepted and used | - Prepare policy conditions for 2007 in accordance with the documentation of donor and World Bank budget support for P135-II. - Establish Partnership Committee. - Allocate additional ODA; provide guidance on additional ODA implementation. - Prepare disbursement conditions, additional conditions after the negotiation. | X X X | X X X X | X | X | CEM | Relevant ministries and agencies (MARD, MOF, MOC…) |
| 6 | 7 years of P135-II implementation evaluated | - P135-II Steering Committee meeting. - Organize evaluation workshop. | X |  |  |  | CEM | MOLISA |
| 7 | “Commune cluster center” Project evaluated | - Organize evaluation workshop |  | X |  |  | CEM | MPI |
| 8 | P135-II Roadmap issued and implemented | - Prepare draft Decision to issue the Roadmap for P135-II by CEM (as authorized by the Prime Minister). - Guide localities to develop provincial roadmaps, based on which prepare plans, implement the plans and report the progress. | X | X |  |  | CEM |  |
| 9 | Other | - Check and supervise the implementation; research; consult, organize technical workshops at localities. | X | X | X | X | CEM and relevant ministries and agencies |  |
| II. Capacity Building and Communication |  |
| 1 | Capacity building framework for P135-II | - Finalize the Capacity building framework for commune staff under P135-II - Guide localities to identify needs, prepare capacity building plans under P135-II. | X | X | X |  | CEM | relevant ministries and agencies |
| 2 | Training materials for different aspects and different targeted groups under P135-II (Production Development, Infrastructure, Capacity building, Living standard improvement and social service development) developed and issued | - Research to develop training materials - Training Workshops in some localities - Finalize and print materials - TOT training | X | X X | X X | X | CEM | MARD, MOC, MPI, MOF |
| 3 | Implementation guidelines for local management staff developed for the following components under P135-II: Production development Infrastructure Capacity building: planning, implementation. Living standard improvement and social service development Participatory planning | - Collect, review existing materials, research to propose contents and formats of training manuals - Develop training manuals - Consult and pilot-test in some localities - Print (finalize), disseminate and issue | X | X X X | X X X X | X | CEM | Relevant ministries and agencies (MARD, MOF, MOC…) |
| 4 | Manual for people and communities in monitoring, participation and implementation of P135 developed | - Collect and review existing materials, research to propose contents and formats of the manual - Develop the manual - Consult and pilot-test in some localities - Print (finalize), disseminate and issue | X | X X | X X |  | CEM | Relevant ministries and agencies |
| 5 | Localities guided in developing and implementing communication plans | - Develop, finalize communication plans and issue guidelines for localities to develop communication plans - Implement communication and propagation activities on VTV, VOV and mass media - Research and implement some communication models at localities. | X X | X X | X X | X X | CEM and relevant ministries and agencies | VTV, VOV, newspaper and media |
| 6 | Website for P135-II developed and implemented (http:www.135.com.vn) | -Design -Develop proposal -Test -Finalize and implement | X | X | X X | X X | CEM |  |
| 7 | Indicators and reporting formats for M&E system | - Evaluate, develop and finalize the indicators - Test, finalize and issue | X |  |  |  | CEM | GSO |
| 8 | Management Information System for (MIS) P135-II | - Research and develop MIS system based on VAMESP system - Develop guidelines for information management and consolidated reports for Program 135-II | X | X | X | X | CEM | GSO |
| 9 | Baseline survey | - Design baseline survey - Implement the survey, process data - Workshop and dissemination for Program impact evaluation. | X | X X | X X |  | CEM | GSO |
| III. Production development |
| 1 | Localities guided in financial management, reporting and payment settlement under P135-II. | - Training in MARD’s guidelines (can be integrated with other themes in the same training course) |  | X |  |  | MARD | CEM |
| 2 | Localities (commune level) guided in participatory planning for transformation of the rural economy. | - Research and propose procedures for production development planning and guide localities in production development planning. - Research and develop production development models and share information and experience |  | X X | X |  | MARD | CEM |
| 3 | Guidelines for household groups for management and utilization of assets developed under the Component | - Research and develop guidelines for groups of households for management and utilization of assets developed under the Component |  | X | X |  | MARD | CEM |
| IV. Infrastructure |
| 1 | Guidelines for assessing commune investment ownership for infrastructure component | - Research and propose criteria and procedures for assessing commune investment ownership for infrastructure component under P135-II | X | X |  |  | CEM | MOC |
| 2 | Guidelines for participatory infrastructure O&M | - Research relevant issues and propose solutions - Workshop, consultation and experience sharing in O&M - Study tour to learn and apply best practices in P135-II |  | X X X | X X |  | MOC | CEM MOF MPI |
| 3 | Investment cost norms and reference rates for P135 infrastructure planning (for investment plan preparation, project management...) | - Survey, status evaluation (identify problems, solutions and best practices…) - Develop guidelines (may collect more information for the guide manual) |  | X X | X X |  | MOC | CEM |
| V. Living standard improvement |
| 1 | Guidelines for the Support to services and living standard improvement component developed | - Submit to the Prime Minister - Issue the guidelines | X | X X |  |  | CEM | Relevant ministries and agencies |
| 2 | Research to remove barriers and improve people’s access to services and policies offered by the Program, guidelines for integration and orientation of social policies for P135-II targeted groups | - Implement survey, status evaluation (identify problems, solutions and best practices …) to use as input for guidelines for targeting. |  | X X | X X | X X | CEM | Relevant ministries and agencies |

Committee for Ethnic Minority Affairs