GCAP Vietnam 2007 (Revised June )

|  | Objective(s) and Target group(s) | Activities & Key messages | Time | Organised by | Partner/Execution | BudgetUSD |
| --- | --- | --- | --- | --- | --- | --- |
|  | Operation and Information Sharing |  |  |  |  |  |
| I | Increase information sharing on GCAP Vietnam | Develop, establish and maintaing website, Enhace coordination of GCAP national coalition | June to December | Vietnamese Fatherland Front and the NGO RC | Support from AAV? | 10,000 |
| II | Enhance corrdination of GCAP Vietnam | Enhace coordination of GCAP national coalition | Monthly | Vietnamese Fatherland Front | Support from AAV? | 2,000 |
| III | Secretariat, coordinator, and website | Enhace coordination of GCAP national coalition | Monthly |  | Support from AAV? | According to contract |

|  | Objective(s) and Target group(s) | Activities & Key messages | Time | Organised by | Partner/Execution | BudgetUSD |
| --- | --- | --- | --- | --- | --- | --- |
|  | Awareness Raising |  |  |  |  |  |
| 1 | Enhance awareness among the public and organizations about the root causes for hunger and poverty, and remedies for hunger and poverty reduction. Target group: general public, focus on ethnic minorities, farmers and women Key messages: ? | Newspaper articles about GCAP themes Report and discussion forum on selected VTV1 programmes “Vì Người nghèo” (For the Poor), and “Đại Đoàn kết” (Great Unity) Make short film to raise awareness about the causes of hunger and poverty Production of White Bands (Could be combined with activity XX) | All year | Vietnamese Fatherland Front Save the Children UK could provide technical and financial support | Newspapers & magazines: Nhan dan, Thanh nien, Tuoi tre, Dai Doan ket, VFF magazine Vietnam Television | 10,000 |
|  | Awareness Raising and Mobilisation |  |  |  |  |  |
| 2 | Enhance public awareness on the root causes for hunger and poverty, and mobilise broad participation of society in hunger eradication & poverty reduction work, and GCAP campaign Target group: secondary pupils and high scholl students Key messages: ? | Arrange contest about GCAP campaign | July | Vietnamese Fatherland Front Support from OGB? | Adolescent Academy | 5,000 |
| 3 | Enhance public awareness on the root causes for hunger and poverty, and mobilise broad participation of society in hunger eradication & poverty reduction work Target group: Residents in 5 residential areas, in Bac Giang, Nam Dinh, Tay Ninh, Hue, and Hai Duong Key messages: ??? | Communicate information on issues relating to GCAP during the Great Unity Festival in residential areas | November | Vietnamese Fatherland Front Support from AAV? | Vietnamese Fatherland Front | 5,000 |
| 4 | Enhance public awareness on the root causes for hunger and poverty, and mobilise broad contributions to hunger eradication & poverty reduction work Target group: the general public, private enterprises, key policy makers??? Key messages: ??? | Participate in the “Nối vòng tay lớn” (Grant Solidarity) event on December 31. (Is it possible to organise session where key policy makers discuss poverty issues) | December 31 | Vietnamese Fatherland Front | Vietnam Television | 30,000 |
| 5 | Enhance public awareness on the root causes for hunger and poverty, and mobilise broad participation of society in hunger eradication & poverty reduction work Target group: Resident in the Red River area Key messages: ??? | Promote the GCAP campaign through the “Đua xeđạp đồng bằng Sông Hồng" (Hong River Delta Bicycle Race) | June | Vietnamese Fatherland Front | Gymnastic & Sport Committee Vietnam Television | 10,000 |
| ? | Take part in and contribute to the global: Stand-up and Speak out activity Target group: Global level, National GOV, general public, ??? Key messages: similar to the global messages | Organise Stand-up and Speak out activites | GCAP month of action | Vietnamese Fatherland Front |  |  |
|  | Capacity Building |  |  |  |  |  |
| 6 | Increase understanding on present poverty issues in Vietnam, GCAP and MDGs/VDGs, and discuss success of national guidelines, policies, and targeted programs on hunger eradication & poverty reduction Target group: the VFF and the GCAP National Coalition Key messages: ??? | Arrange seminar on hunger eradication, poverty reduction policies and programs, and implementation of MDGs/VDGs and GCAP in Vietnam (Should wait until the report on MDG is produced in order to utilize report findings) | July | Vietnamese Fatherland Front (input from Mina) Support from AAV? | Vietnamese Fatherland Front | 3,000 |
| 7 | Enhance public awareness and mobilise active contributions from society towards hunger & poverty eradication work Target group: the general public Key messages: ??? | Arrange a Performance for the Poor at VTV1 studio or at the Sports Hall in Hai Ba Trung district to mark the Vietnamese Day for the Poor (October 17). This performance shall be broadcast and all revenue from sale of tickets will be contributed to the Fund for the Poor. | October 15 | Vietnamese Fatherland Front | Vietnam Television | 20,000 |
|  | Monitoring & Policy Advocacy |  |  |  |  |  |
| 8 | Influence the creation of pro-poor policies, enhance public awareness of the causes of hunger and poverty, thereby mobilising broad participation from the whole society in hunger eradication & poverty reduction work Target group: ? Key messages: ? | Make written contribution and organise dialogues with key policy makers to contribute to legislation development in relation to poverty reduction, people's participation, grass-roots democracy. Etc. (Could be combined with above activities such as VTV programme) | All year | Vietnamese Fatherland Front Support from VECO | Democratic and legal board? | 5,000 |
| ? | Monitor Vietnam's progres on implementation of selecled off-track MDGs/VDGs Target group: National GOV and policy makers? | Produce a Monitoring Report on 1 or 2 off-track MDGs/VDGs (research or analysis of secondary data) | May/June | Vietnamese Fatherland Front NGO RC, AAV, Save The Children UK could provide technical support | ? | ? |
|  | In all |  |  |  |  | 60,000 |